## Summary-GroupIterationProgress
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed & in test | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/7-9/9 | - Finalized initial team role assignments -Decided on project scope: convert Kimleng's existing console-based POS application into a web application using Spring Boot and Angular, reusing existing functionality and adding new value on top rather than starting from scratch -Selected tooling for tracking and documentation (GitHub Projects, Trello, Google Drive) and communication (Discord) -Reviewed Iteration 0deliverables and assigned document ownership -Set a recurring weekly team meeting (Sundays 1-2 PM EST). | - Krizma and Italia were delayed to join the github | - Had a hard time understanding and assigning team roles; mainly due the fact that a we were mostly unsure of what each role consisted of, but it was ironed out during our second team meeting | - We came up with a recurring time for our weekly meetings -Discussed general responsibilities moving forward -We have a good starting point for the project; using Kimleng's initial POS dashboard project | - | - | 8 | 8 | 0 | 30.75 | 22.25 | 8.5 | 7 | 5.5 | 0.75 | 0 | 1 | 5.5 | 1 | N/A
1 | 9/10-9/21 | - Finalized MySQL as db - set up 3 container docker dev environment: MySQL 8.4, SpringBoot (Java21), Angular Web - Established Docker Compose workflow for local development, including clean build and volume/image cleanup steps - Documented Clean Architecture approach - domain layer framework agnostic, business logic and repositories in middle layer - scoped iteration1 down to authentication only (login, logout, main screen), deferring the web checkout interface baseline and product catalog API to iteration 2 - Scaffolded the SpringBoot app and the web folder for Angular, with Docker Compose and a Dockerfile for the API (PR #16, merged) - Built JWT authentication framework with Spring Security (PR #31), fixed the bugs, and merged to develop branch - Refactored backend security configuration and user details handling to align with Clean Architecture, including CORS fixes for the webUI (PR #78) - Added Scalar UI for API docs and PlantUML diagrams to api/docs (PR #80) - Added JUnit tests to Github Actions CI pipeline and removed a leftover test skeleton - Implemented Feature 18, in testing right now - Built out epics and user stories for every feature in the SPPP and grouped them accordingly - Created "User Authentication & RBAC" epic and added user stories to it - Login credentials for testing were established - Scaffolded the Angular project, added CORS proxy configuration, and built a login form component - Added frontend to Docker compose and Dockerfile, getting the UI running - Team demoed working login functionality at the 9/20 meeting - Set up Github Actions CI/CD pipleine for backend API; frontend pipeline deployment was still pending - Resolved a proxy/localhost API configuration issue so the API container routes correctly - Added a full system test as a GitHub issue (#81) as a template for the team - Testing policy established: each person unit-tests their own stories with a pass and fail scenario; a first-pass system test by the implementer, second pass verified by QA Lead (Italia) - GitHub Projects workflow completely set up - Kimleng took lead on SDD, Italia took lead on STD - Updated SPPP - Team voted on a hybrid API documentation/testing approach (Scalar for docs, Postman for automated tests) | - Docker/database connection errors (9/20 meeting): Italia and Kimleng had the API and web containers fail to start properly; team saw a 500 connection error despite a successful login. Andy's setup worked, theirs didn't — inconsistent environments across machines (fixed) - API localhost/proxy configuration: needed a new proxy config to correctly route API traffic to the container; Kimleng proposed an NGINX alternative for local dev to avoid frequent redeployments. Resolved by Andy and Sara per the summary - CORS issues: Sara's PR #78 was explicitly a security update to align CORS with the web UI after Kimleng's frontend PR merged. - Leftover/broken test skeleton: Sara found and deleted a stale test skeleton when wiring JUnit into CI (fixed) - Long initial build times: Sara flagged that the first Docker Compose build takes a while due to downloading Angular/MySQL dependencies, and recommended cleaning up volumes/images after tearing down | None | - Scope discipline: the team explicitly narrowed Iteration 1 to authentication only (login, logout, main screen) and pushed the checkout interface and product catalog API to Iteration 2 — a deliberate move to avoid overcommitting, made at the 9/20 meeting and assigned to Sara to reflect in the SPPP - Two-pass testing policy: the STD's Testing Summary establishes that each person unit-tests their own stories (pass + fail scenario minimum), and every feature gets a first-pass system test from the implementer and a second-pass verification from the QA lead (Italia). This is a formal process, not just a one-off habit - Shared test-case template: Italia posted issue #81 as a system-test template specifically so others would reuse the same structure rather than inventing their own each time - Epic-based backlog organization: Krizma and Sara moved from a flat story list to grouping every story under epics aligned to the SPPP, with a rule to keep labels identical to the SPPP wording "to alleviate confusion." - PR-based code review became the norm: every merge from 9/13 onward (PRs #16, #31, #76-#80) went through review comments before merging - Standardized tooling decision: the team ran an actual poll to settle on Postman + Scalar hybrid for API docs/testing, replacing ad hoc individual choices - CI enforcement of tests: Sara wired JUnit tests into GitHub Actions so tests run automatically on the backend, and removed a stale test skeleton that was cluttering the suite | 13 | 4 | 69 | 22 | 47 | 77.5 | 68 | 9.5 | 9 | 12.5 | 5 | 10.5 | 4 | 9.5 | 10.5 | N/A
2 | 9/22-10/5 | - Iteration 1 submitted 9/22 (Iteration 1 release merged to main, PR #83; meeting minutes added to GitHub, PR #82) - Reviewed Iteration 1 feedback and the facilitator's project analysis at the 9/27 meeting and assigned fixes - Estimated story points for the Iteration 2 backlog using planning poker (Fibonacci scale); #18 set at 3 points, checkout at 8 - Set up CI for both frontend and backend on develop and main, and fixed failing frontend tests (#88, PRs #86-#91) - Set up continuous deployment to an AWS EC2 server through GitHub Actions; the app and Scalar API docs are publicly reachable (PRs #92-#94) - Added JaCoCo backend code coverage (PR #104) and code coverage reporting in the GitHub Actions summary (PR #110) - Built the Angular web UI foundation: Angular Material, app layout, sidebar routing, and feature modules for product, inventory, sale, user, and report (PR #95) - Built Product Catalog Management for #22 and #23: product and category endpoints, search by barcode, and frontend pages with tests (PR #96) - Added integration tests for the seeded admin, manager, and cashier users (#60, PR #98) - Built the user view and create user pages with an admin guard (#32 and #37, PR #101) - Built the core inventory report for Admin and Manager roles (#57, PR #100) - Added a CODEOWNERS file (PR #99) - Enabled the Test Request button on the Scalar API docs page - Reformatted all meeting minutes into one template (purpose, agenda, discussion, action items, collaboration, summary) - Started the final presentation plan (three videos) and split sections by role | - EC2 deployment failing after PR #95 because the server ran out of disk space ("no space left on device" while building the web image); PR #109 attempted a fix, still failing on 10/5, Andy asked to clean up the server's disk - Frontend Docker build failing locally after updating develop (Angular CLI not installed in the image); Italia worked around it - Vitest frontend coverage errors in the GitHub Actions summary, while JaCoCo backend coverage works - Merge conflicts in GlobalExceptionHandler because several PRs added the same method; Sara resolved them while merging - Browser localStorage not available in CI, fixed by mocking in-memory storage - Stories #49, #19, and #17 blocked waiting on manager-access endpoints - Dependabot dependency-update PRs failing tests | - Iteration 1 submission was delayed waiting on the presentation slides, videos, document sign-offs, and one progress report tab - Several stories were moved to Iteration 3 because of dependencies (#48, execute sale, #19, #17, low-stock alerts, account switching, price check) - Unclear expectations for the AI usage section and code walkthrough in the final presentation (Sara asking the professor) | - Estimated story points for every Iteration 2 story with planning poker, fixing the biggest point loss from Iteration 1 - Extended the 9/27 meeting to 2 hours to cover feedback, CI/CD, estimation, and Lab 3 - Before each submission, the team meets to review all feedback for completeness - Agreed to check in on Discord at least every other day - Set a PR deadline (6 PM 10/5) with a review window (6-10 PM) so every PR gets reviewed before the release - Added CODEOWNERS to enforce reviewers on PRs - Code coverage now reported automatically in CI - One meeting minutes template for every meeting, with discussion, decisions, and action items - Everyone updates their own progress report tab without overwriting formulas - Iteration 3 focuses on core features, combining several reports into one, instead of the AI features | 26 | 31 | 72 | 26 | 46 | 96.5 | 83.5 | 13 | 9.5 | 4.5 | 7 | 26 | 15.5 | 7.5 | 8.5 | N/A
3 | 10/6 - 10/12 | - Iteration 2 submitted; reviewed Iteration 2 feedback at the 10/10 meeting (minor deductions: SDD class diagrams, security class names, risk register scores, AI headers) - Sales report by date range (#29, PR #133) and product level sales analysis (#30, PR #144) - Update user role and enabled status (#19, PR #146) and navigation updates for non-Admin users (PR #145) - Execute sale, frontend and backend (#46, PR #155) - Inline price and stock editing on the Inventory page (#148, PR #156) - Print receipt (PR #157, #158) - Refactored the report components for a consistent UI (PR #153) and fixed the product pagination total count (PR #154) - Moved secrets and passwords out of the property files (#85, PR #150) and updated the READMEs (PR #151) - Fixed disabled users getting a 500 instead of 401 at login (PR #152) - Test stories opened for every story, using Italia's template (#134-#142, #149); system tests closed for #18, #19, #23, #24, #57 and user creation - Final presentation slide deck built, with a Project Vision slide and a project-wide AI Usage slide - Final Project Videos folder created for each member's presentation and code walkthrough/demo videos | - Disabled users got a 500 error instead of 401 at login, and the JWT filter didn't check if a user was enabled (found in the PR #146 review; fixed in PR #152) - The 15-minute idle timer only starts on the dashboard page, so other pages don't time out (found during #18 system testing) - Products seeded by V3 all have 0.00 prices, so the sales report needed its own QA seed data - Product table pagination showed the wrong total count (fixed in PR #154) - Secrets were stored in the property yml files and had to be moved out before the AWS deployment (PR #150) - #30 was built on top of the #29 branch and had to be retargeted to develop after #29 merged | - Short final iteration: one week, with deliverables due Tuesday - Cost vs. selling price confusion (15% markup) on the products table; the team agreed to remove the price column and manage pricing on the Inventory page - Coordinating each member's two videos (presentation and code walkthrough/demo) with cameras on - Several stories stayed open waiting on their system test pass (#29, #30, execute sale, print receipt) | - Every story gets a [TEST] issue using Italia's template before it can move to Done - Two-pass system testing: the implementer does the first pass, QA (Italia) does the second - One story built with the test-first method, noted in its PR description - Requirements Leader (Krizma) tracks story and test status so nothing is marked Done untested - Rotate the minutes taker each iteration (from Iteration 2 feedback) - AI usage headers added across all project files; project-wide AI usage summarized in the final presentation - All documents updated and signed by every member before submission | 17 | 0 | 0 | 17 | 0 | 64 | 56 | 8 | 5.5 | 2.5 | 2.5 | 17 | 11 | 11 | 3.5

## AIUsageLog
This sheet records all AI usage by your team members
Who | When | Tools | Tasks & Artifact | Final Use (Accepted / Modified / Rejected) | Evaluation/Modification | Link /Appendix/ Prompt history + output summary
Sara | 2026-09-09 | Gemini | Development of an Agile GitHub Projects cheat sheet, monorepo directory layout, and dual iteration/milestone tracking rules. | Accepted | Specified functional folder names (code/api, code/web), selected Maven over Gradle, aligned sprint terminology with course expectations, and reordered best practice rules. | Gemini provided a GitHub Projects crash course, created issue templates, structured a full-stack Spring Boot/Angular repo, and established sprint tracking rules. Sara AI Usage Log
Sara | 2026-09-11 | Gemini | Brainstormed ideas to share with team during next standup meeting | Modified | Made modifications based on personal preference and drove conversation towards the outcome I was expecting. | Created a meeting agenda to go over the feedback from our first iteration submission and prepare for the lab 2 and iteration 1 development.
Sara | 2026-09-12 | Gemini | Creation of a structured 120-minute team meeting agenda and GitHub workflow guidelines for Iteration 1 kickoff. | Accepted | Expanded meeting duration to 2 hours, clarified GitHub Projects usage over Jira, provided raw Markdown after binary upload issues, and integrated Lab 2 rules. | Gemini helped transform a basic agenda draft into a comprehensive 2-hour plan addressing Lab 2 criteria, role rotations, and project board rules. Sara AI Usage Log
Andy | 2026-09-13 | google.ai | Create dockerfile and docker-compose | Accepted | works fine | make one dockerfile to have both mysql and springboot runtime
Sara | 2026-09-13 | Gemini | Designed a multi-container Docker setup for Spring Boot 3, MySQL 8.4, Flyway, and Angular, producing orchestration files and a root README.md. | Accepted | Started with Andy's docker files. Defined monorepo structure, incorporated Flyway, updated stack versions, requested IDE setup steps, and temporarily commented out the web container. | Advises on build sequence and monorepo structure for containerizing Spring Boot and Angular, generating a repository README.md. Sara AI Usage Log
Kimleng | 2026-09-13 | Github Copilot | Verify if Bluejay web api is running correctly | Modified | Initially I ask for creating root url to display hello world message but it's end up with the spring application already turn on security by default. This means that I can see login page and verify if app is running. | Summary: Confirmed the app was already running, and the login prompt was coming from Spring Security’s default behavior, not from custom auth code in your project. What AI helped me figure out: 1.spring-boot-starter-security in api/pom.xml is what enables the default login page. 2.There was no custom security setup in your codebase for username/password. 3.The default credentials are: ◦ username: user ◦ password: the generated value printed in startup logs 4. If you run with Docker Compose, the startup logs are in: ◦ docker compose logs api ◦ or live: docker compose logs -f api 5. A custom hello-world endpoint was not necessary just to verify the app is up, since the app already proved it was running by serving the Spring Security login page.
Kimleng | 2026-09-13 | Copliot Agent | Plan for migration jpos to bluejay | Rejected | I let AI agent explore jpos project with specific directions including technologies, existing modules, and specific code areas for starting points. It comes up with the large PR that is hard for code review and burn my credit about 328.4. It had redefined and minimized requirement 3 times. | Summary: 1. Explored your current JPOS codebase (especially InventoryFacade, UserFacade, SaleFacade, and ReportFacade) and mapped legacy behaviors. 2. Built a first-iteration BlueJay backend API foundation using Spring Boot. 3. Added stateless JWT authentication (as requested) and kept existing role permissions unchanged. 4. Wired dependency injection for core modules with Spring. 5. Exposed REST endpoints for: ◦ auth ◦ user ◦ inventory ◦ sale ◦ report 6. Kept report export behavior in place for now (postponed redesign). 7. Removed hardcoded security-sensitive defaults and moved key settings to environment-based config. 8. Added schema/bootstrap support for the API runtime and improved JDBC provider structure to make DB switching easier later. 9. Ran validations: ◦ tests passing (mvn clean test) ◦ secret scan passed ◦ code/security validation run and fixes applied from findings.
Kimleng | 2026-09-14 | Google Gemini | Collaborated on transform software requirement into a structured production-ready Agile backlog | Accepted | I evaluated and modified the project plan by clarifying user roles and required data fields, consolidating Stock Entry and Stock Entry Validation into a single user story, and enforcing the Given-When-Then format for all acceptance criteria. I also simplified the project overview language to make it easy to communicate with business stakeholders, and I explicitly aligned the developer tasks with tech stack (Angular, Spring Boot, MySQL, and Clean Architecture) by grouping them into domain-specific Technical Breakdowns structured as vertical slices. | Summary: 1. A Single Unified Epic: Established the Catalog & Stock Management System (CSMS) to centralize all product and inventory requirements under one roof. 2. A Stakeholder-Approved Overview: Written in simple, non-technical language to make it easy for you to communicate the system's value to business partners. 3. Behavior-Driven User Stories: Built out complete requirements for adding products, viewing the catalog, executing verified stock entries, and automating real-time post-sale deductions. 4. Standardized "Given-When-Then" Criteria: Rewritten all acceptance criteria into explicit testing boundaries so the team knows exactly when a feature is considered "Done." 5. Domain-Specific Technical Breakdowns: Tailored developer steps directly to the architectural layers (Angular, Spring Boot, MySQL, and Clean Architecture) as actionable vertical slices. 6. Plain-Language Developer Summaries: Appended a clear, high-level overview to every engineering task so team can easily track and explain what developers are building at any given time.
Kimleng | 2026-09-15 | Google Gemini | Evaluating Modern Cloud Identity Architectures for Multi-Framework Ecosystems | Modified | I steered the conversation by systematically breaking down JWT mechanics and testing third-party authentication options to eliminate password storage liability. I first validated my backend database assumptions, then rejected Google Cloud and Auth0 after discovering their limitations with free, dashboard-driven role management for my small team. I pivoted the design toward Microsoft Entra External ID to get native Google login proofed the entire architecture by introducing my upcoming migration to Java and Spring Boot, verifying that open standards will keep my identity layer completely decoupled from my backend framework. | Summary: 1. Understand that JSON Web Tokens function like a digital passport, allowing my backend to verify identity and permissions strictly via cryptographic signatures without looking up users in a database on every request. 2. Realize that offloading authentication to a third party does not mean losing authorization control, as my API can still enforce custom roles based on data embedded in the token. 3. Discover that Google Cloud requires writing custom code or scripts to manage user roles, making it less ideal for a quick, zero-database setup. 4. Learn that Auth0 provides an excellent user management dashboard but locks standard Role-Based Access Control (RBAC) behind a $35/month paywall. 5. Identify Microsoft Entra External ID as the optimal solution because it provides a visual portal to define and assign roles (Admin, Cashier, and Stock Manager) completely for free up to 50,000 monthly active users. 6. Confirm that local development remains perfectly smooth with cloud identity providers by utilizing standard localhost redirect URIs and secure HTTPS developer certificates. 7. Recognize that building an authentication layer entirely on open standards (OAuth2 and OpenID Connect) keeps my architecture framework-agnostic, ensuring a seamless future migration from ASP.NET Core to Java Spring Boot.
Krizma | 2026-09-13 | Claude | Wrote user stories for Lab 2 with breakdown tasks and acceptance tests | Modified | - Evaluation / Modification: The story descriptions were my own choices. I checked that each story followed INVEST, that they didn't overlap with my teammates' stories, and that the tasks matched our Spring Boot and Angular stack. I edited the tasks and tests before adding them to Jira. | - Prompt summary: I asked for a step-by-step plan for Lab 2. I then supplied the two stories (Sale Report by Date Range and Product-Level Sale Analysis) in As a/I want/So that form and asked Claude to write them up for step 2, with a breakdown, story-point estimate and acceptance tests. - Output summary: Claude returned a title, description and story-point estimate for each story. Story 1 (Sale Report by Date Range) was 5 points. Its tasks were designing the query, building a GET /reports/sales?start=&end= endpoint, adding an Admin-only role guard, calculating revenue, cost and net profit, building a date-range picker and summary display, writing unit tests (data in range, empty range, invalid range), and manual QA. Its acceptance tests were an Admin getting totals for a period, and a Cashier being rejected with a 403.
Krizma | 2026-09-13 | Claude | Docker Setup Troubleshooting | Accepted | - Evaluation / Modification: The fixes worked when I applied them. I ran the build and run steps myself and took the report screenshots. | - Prompt summary: I asked whether I needed the docker.sbx package I had installed with winget, then reported a virtualization-not-detected error, a Dockerfile.txt file that wouldn't build, and a failed build. I also asked for the commands to access and manage the containers. - Output summary: Claude explained that docker.sbx is Docker Sandboxes, not Docker Desktop, and told me to uninstall it and install Docker.DockerDesktop (or use the direct download). It gave the WSL2 and BIOS virtualization steps, the fix for the .txt extension Notepad added, and the reminder to start Docker Desktop before building. It also covered docker exec -it, docker inspect and docker logs, and how to verify with docker --version and docker run hello-world.
Krizma | 2026-09-16 | Claude | SPPP Backlog Audit - pulled the live github issues that compared them against the SPPP feature list to find what already existed and what was missing | Modified | Evaluation / Modification: I checked Claude's list against GitHub Projects board #32 myself to confirm it matched, and confirmed with Kimleng which stories he was already drafting so we didn't duplicate work. | Prompt summary: I asked Claude to review the team's live GitHub issues and tell me which features from the SPPP already had epics or stories and which had none. Output summary: Claude listed the existing items: epics #20 (Auth/RBAC) and #21 (Catalog & Stock), and stories #14, #15, #17-#19, #22-#25, #29-#30, #32-#33 and #47. It mapped them against all 24 SPPP features across the Essential, Desirable, Existing and Optional tiers and identified the gaps: Admin Preloading, Core Inventory Report, Inventory Report by Date Range, Stock Entry Validation, and all four optional features.
Krizma | 2026-09-17 | Claude | Drafting epics and missing user stories - defined the epic structure for the backlog and drafted full user stories for every gap found in the audit | Modified | Evaluation / Modification: I checked that each of the 24 SPPP features fit under exactly one epic and reviewed every story for INVEST compliance. Claude noted that the Multi-Location epic has a single optional story and could fold into Catalog & Stock, so I raised that with the team instead of deciding alone. I edited story points and acceptance tests before adding anything to the board, and coordinated with Kimleng so we didn't create duplicate or contradictory stories. | Prompt summary: Following the audit, I asked Claude to group the full feature list into epics that would work as the top level of the GitHub Projects board, building on the two epics that already existed. I then asked it to write complete stories for all the missing features in the same format as the existing ones, including breakdown tasks, story points and acceptance tests. Output summary: Claude defined six epics: User Authentication & RBAC, Catalog & Stock Management, POS Checkout, Sales & Financial Reporting, AI-Driven Automation, and Multi-Location Expansion. It assigned every SPPP feature to one of them and flagged the option of folding Multi-Location into Catalog & Stock. It then wrote stories for Admin Preloading, Core Inventory Report, Inventory Report by Date Range, Stock Entry Validation and the four optional features. Each has an As a/I want/So that statement, breakdown tasks, a story-point estimate and two Given/When/Then acceptance tests.
Krizma | 9/18/2026 - 9/20/2026 | Claude Code | Feature 18 - assisted in implementing feature 18 end to end | Modified | Evaluation / Modification: I followed the team's existing test patterns and ran every test locally. I verified the lockout and the inactivity message in the browser, and added the required AI-USAGE headers and inline comments to each file. I asked Sara to review because the change touches her JWT filter. | Prompt summary: I had no prior experience with this stack. I asked Claude for complete step-by-step guidance through the whole feature: environment setup, the repo structure, branching from develop, writing the code, running tests, checking it in the browser, and opening a PR. Output summary: Claude walked me through installing JDK 21, Node LTS, Docker Desktop and the VS Code extensions. On the backend it produced TokenBlacklistService, a revoked-token check in JwtAuthenticationFilter, and POST /api/v1/auth/logout. On the frontend it produced a logout that calls the server, a 15-minute idle timer, dashboard lifecycle hooks, and the "Session Expired due to inactivity" message on the login page. It also wrote the tests (18 frontend, 19 backend) and helped with the Docker Compose path problem using environment variables. The work went into a PR from feature/18-session-lockout into develop.
Italia | 2026-09-21 | Deek Seek | Manual Testing Section of the STD | Modified | Amended what the AI initially gave to meet what I was looking for to use in the Manual Testing section of the STD | https://chat.deepseek.com/share/c0sh6wslumfo3vztmq Summary: Used AI to pull all the current user stories from the project and render them as a table
Sara | 2026-09-13 | Gemini | Development of Agile user stories, PlantUML RBAC class diagrams, and team collaboration strategies for a POS software project. | Accepted | Updated story scopes to avoid teammate overlap, chose a full RBAC model with PlantUML, and requested strategic messaging to align on local JWT vs. Auth0 and Flyway migrations. | Comprehensive consulting on Agile user story refinement and RBAC data modeling Sara AI Usage Log
Sara | 2026-09-16 | Gemini | API testing tools comparison (Postman vs. Swagger UI vs. Scalar), team poll draft, and Spring Boot integration setup. | Accepted | Requested a feature comparison and team poll question, then steered the model by specifying their Spring Boot framework to get integration instructions. | Compares Postman, Swagger UI, and Scalar for API endpoint testing and provides Spring Boot integration steps using springdoc-openapi. Sara AI Usage Log
Sara | 2026-09-16 | Gemini | Refactoring Java Spring Boot code based on PR review comments, covering exception handling, guard clauses, path matching, Swagger JWT auth, and global error handling. | Accepted | Presented PR review comments, directing the model to adapt path matching for domain packages, and attach course-mandated AI disclosure comments. | Resolves Spring Boot PR review feedback by implementing guard clauses, global path prefixing, and OpenAPI JWT authorization. Sara AI Usage Log
Sara | 2026-09-17 | Gemini | Agile user story generation, backlog deduplication into a 3-sprint roadmap, Clean Architecture diagram evaluation, and Spring Security architecture alignment. | Accepted | Directed story generation from legacy facades, instructed the model to deduplicate GitHub issues favoring lowest issue numbers, created a 3-sprint roadmap, and drafted team architecture feedback. | Generates Agile user stories, deduplicates a 25-story backlog into a 3-sprint roadmap, and evaluates Clean Architecture / DDD alignment for a POS migration project. Sara AI Usage Log
Sara | 2026-09-20 | Gemini | Clarified Spring Security password encoding logic, HTTPS security, Docker networking, and AWS vs Azure cloud deployment options. | Accepted | Expanded the scope from local password verification code to HTTPS security theory, container isolation, and cloud load balancer cost/complexity comparisons. | Explains Spring Security password matching and HTTPS security, transitioning to container networking and AWS/Azure deployment architecture. Sara AI Usage Log
Sara | 2026-09-20 | Gemini | Evaluated executing Docker Compose in GitHub Actions pipelines and produced CI/CD workflow configurations for testing and caching. | Accepted | Directed the AI from basic CLI runner support to host vs. container testing trade-offs, leading to concrete Maven and npm caching setups. | Demonstrates running Docker Compose in GitHub Actions CI pipelines and optimizing build performance through host-based dependency caching. Sara AI Usage Log
Sara | 2026-09-20 | Gemini | Drafted Software Design Document (SDD) sections covering Security Design, PlantUML sequence diagrams, and design patterns. | Modified | Instructed the AI to populate SDD sections from a PlantUML class diagram, requested sequence diagrams, directed table streamlining, and expanded into design patterns. | Populates and refines Security Design and Design Patterns sections of an SDD based on PlantUML diagrams and Clean Architecture principles. Sara AI Usage Log
Sara | 2026-09-20 | Gemini | Integrated Scalar API UI in Spring Boot, resolved security and 401/404 routing errors, optimized Docker build caching, and configured Actuator endpoints. | Modified | Steered choices toward unauthenticated UI with Postman testing, eliminated redundant Docker builds, and fixed Actuator YAML formatting. | Guides integration of Scalar API UI with Spring Boot, addressing Spring Security, Docker Compose caching, IDE run configurations, and Actuator endpoints. Sara AI Usage Log
Italia | 2026-09-22 | Deek Seek | Summary for Team 1 Progress Report for the Iteration 1 presentation | Modified | Amended what the AI gave to be more high level | https://chat.deepseek.com/share/1ecpithd47dg0c23av Summary: Asked the AI to summarized what was written in the group summary tab to help write the iteration 1 presentation
Andy | 2026-09-26 | Google.ai | Output format for CI/CD yml configuration file, ask how to set up secrets | Modified | CI/CD yml file works fine, Secrets need some tweaking, CI/CD yml file edited to keep it relevant | https://www.google.com/search?aep=11&udm=50&q=Github+Action+run+command+in+SSH
Kimleng | 2026-09-26 | ChatGPT | A prompt for GitHub Copilot to generate Angular foundation & team feature scaffolding project template | Modified | I defined an Angular application foundation for a six-person development team, focusing on modular feature ownship, shared layout and routing, standardized scaffolding, and development conventions to minize code conflict and make parallel development easier. | Prompt summary: 1. How should I set up the Angular sidebar and layout for a 6-person team to reduce code conflict? 2. Can I scaffold all necessary components and routes so everyone can get started easily? 3. How can I have GitHub Copilot implement this step by step?
Kimleng | 2026-09-27 | GitHub Copilot | Create web UI foundation structure | Modified | Iterate over the implementation details and adjust and adapt the structure that make more sense for Bluejay project. | Prompt summary: 1. Create the WebUI structure based on the given prompt. 2. Let refactor feature routes to its own feature directory and tie them up to root routes. 3. Should auth service stay in /core/auth or or /core/service/auth?
Kimleng | 2026-10-03 | Github Copilot | Implement database persistant, API controller, and tests including unit test and integration test | Modified | Constantly evaluate the output results with the design decision, workflow, structure around product catalog. | Prompt summary: 1. Implement product and category repository by extending JPA repository. 2. Let refactor mock product, and category repository to mockito 3. Create 3 components product-search, product-list and product-form and place them in product-page. Layout them in two columns and using Angular Material component as much as possible
Kimleng | 2026-10-04 | Microsoft Copilot | Create an consistancy meeting minutes with well defined sections including purpose, agenda, action items, collaboration, and summary | Modified | Output in Microsoft Word mis-matched with Google Doc and manually format tabs, font, bulletpoints, and spaces | Prompt summary: 1. There are an inconsistancy in meeting 5, 4, 3. Let read and understand the meeting and create agenda, and summary section. Take meeting 1 and 2 as example.
Krizma | 2026-09-25 | Claude | Feature 18 PR review follow up - adding a logged out confirmation message to feature 18 after Sara's PR review (PR #79) | Modified | Sara suggested the change in her review. I applied it, reran the frontend tets, and checked the message in the browser before pushing the update to the PR. | I asked Claude to implement the PR review suggestion to show a confirmation message after a manual logout. Claude helped me add a reason=logout redirect to the login page with a confirmation message, and two new component spec files to test it.
Krizma | 2026-10-03 | Claude | User story #57: Core Inventory Report + PR Review | Modified | I applied the changes locally and found test files had landed in src/main instead of src/test, which caused compile errors. I located and moved them with PowerShell (Get-ChildItem / Select-String) and fixed the package declarations. I ran all 25 backend and 30 frontend tests and confirmed they passed before pushing. I opened the PR myself; nothing was pushed by the AI. | Prompt summary: Implement the core inventory report story with exact file paths and full code, then help debug the build errors I hit while applying it. Output summary: GET /api/v1/reports/inventory restricted to Admin/Manager, an AccessDeniedException handler in GlobalExceptionHandler (fixed unauthorized requests returning 500 instead of 403), an Angular Reports page with loading/empty/forbidden states, and backend and frontend tests.
Krizma | 2026-10-03 | Claude | User story #29: Sales Report by Date Range (sub-issues #40, #41) - backend endpoint, Angular page, tests, and manual QA seed script | Modified | The AI could not run the backend tests in its own environment, so I applied the changes locally and ran mvnw test myself, which passed. I updated the "pending" verification notes in the test files with the real results before committing. I checked that the report uses each sale's recorded price and cost, as described in our schema notes, and that a Manager login is blocked from the page. I pushed the branch myself. | Prompt summary: Build the sales report by date range on top of the latest develop branch, following the same structure as #57. Output summary: GET /api/v1/reports/sales (Admin only) returning revenue, cost, net profit, transaction count, and units sold, calculated from the price and cost saved with each sale. Invalid or missing dates return 400. An Angular /reports/sales page with date presets and summary tiles, a QA seed script, and backend and frontend tests (98 frontend tests passing).
Krizma | 2026-10-05 | Claude | Progress Report Review - Reviewing the progress report against Iteration 1 feedback: hour totals and formula fixes for the Summary, splitting my week 2/3 hours, drafting weeks 4-5 and AI log entries | Modified | I had Claude read the sheet but not edit it, and I entered every change myself. I checked the corrected Iteration 1 total (about 77 hours) against the facilitator's figure of about 76. I adjusted the drafted hours and descriptions to match the work I actually did. | Prompt summary: Using the Iteration 1 feedback, tell me what's wrong with the hours and formulas, add up the team's hours per iteration, split my week 2 into weeks 2 and 3, and draft weeks 4-5 and my AI log entries. Output summary: Found that the Summary formulas only counted row 5 of each tab, typed-in totals that didn't add up on Andy's and Italia's tabs, and a cell stored as a date. Gave per-iteration totals and drafted weekly entries for me to edit.
Sara | 9/24/2026 - 9/27/2026 | Gemini | Spring Boot JWT security, Docker deployment, AWS Parameter Store proposal, and React secret handling | Accepted | I requested specific configurations (Docker, MySQL, AWS Parameter Store), drafted team communications, and explored enterprise secret strategies. | I secured my Spring Boot app's JWT key by evaluating local environment variables, Docker integration, AWS Parameter Store, and Delinea Secret Server. Sara AI Usage Log
Sara | 2026-09-26 | Gemini | Team 1 meeting agenda for post-Iteration 1 review, backlog refinement, CI/CD, and Lab 3 setup | Accepted | I directed the model to shift meeting focus toward backlog refinement/pointing, add Andy's CI/CD demo, extend to 2 hours, and format as an outline. | I generated a structured 2-hour meeting agenda and run sheet to address Iteration 1 feedback, refine Iteration 2 scope, review AWS CI/CD, and align on Lab 3. Sara AI Usage Log
Sara | 2026-10-03 | Gemini | Integration tests for Flyway admin database seeding with Testcontainers and Spring Boot. | Accepted | Directed the AI to combine test classes, switch to @SpringBootTest, add MySQL 8.4 Testcontainers setup, and apply custom AI attribution header comments. | Created a comprehensive integration test suite verifying database migrations and RBAC user seeding using Spring Boot and MySQL 8.4 Testcontainers. Sara AI Usage Log
Sara | 2026-10-03 | Gemini | Full-stack POS stock entry module using Spring Boot and Angular. | Modified | Instructed the AI to use Java 21 records for DTOs and requested a design discussion regarding schema structure instead of adding a separate table. | Designed and implemented a stock entry feature with quantity and barcode validations, domain-driven architecture, and Angular Reactive Forms UI. Sara AI Usage Log
Sara | 2026-10-03 | Gemini | Full-stack implementation of stock entry flow including Spring Boot backend and Angular frontend components. | Accepted | I instructed the model to follow team package layouts, integrate custom exceptions, support CustomUserDetails, adopt modern Angular @if/@for control flows, and convert hardcoded UI strings to dynamic data models. | Developed a full-stack Spring Boot and Angular stock entry feature with validation, audit logging, and dynamic UI state. Sara AI Usage Log
Sara | 2026-10-03 | Gemini | Clarified admin initialization task requirements and set up @SpringBootTest integration testing strategies | Accepted | I pointed out that I already used Flyway scripts for seeding, steering the discussion toward updating technical tasks and configuring a dedicated test database profile. | I clarified the role of Spring initialization vs. Flyway scripts, updated my user story tasks, and designed an integration testing strategy using a base test class and a dedicated test database. Sara AI Usage Log
Sara | 2026-10-05 | Gemini | Diagnosed integration test failure and supplied solution for duplicate key exceptions. | Accepted | Requested advice on resolving database constraint violations and restructuring tests using actual database data. | Resolved integration test failures by using lazy evaluation and dynamic test data generation. Sara AI Usage Log
Sara | 2026-10-05 | Gemini | Updated Angular routing and guards to enforce the login page as default and block unauthorized access | Accepted | I requested clarification on Angular/Spring route configs and confirmed we already had role guards, leading to refactored guard logic. | I configured app.routes.ts to redirect root/wildcard paths to /login and implemented an authGuard on AppShellComponent to prevent unauthenticated access to protected routes. Sara AI Usage Log
Italia | 2026-10-04 | Github Copilot | Creating the user view list and create a new user form | Modified | AI did great, however had to reprompt to make sure authorization was in place for the APIs and update the CSS to fit with the overall app theme | User List: 37_transcript.md Create User Page: 36_transcript.md
Italia | 2026-10-05 | Github Copilot | Amended front-end and back-end workflow yml files to include testing summary | Accepted | AI did great with what was given and the resulting summary helps a lot in terms of knowing how many tests were in both the frontend and the backend | Prompted AI to update the yml testing files to include the testing summary for each of the PR merges.
Italia | 2026-10-05 | Github Copilot | Amended deployment.yml to try and fix the errors in the deployment pipeline | Modified | AI did decent here at trying to find the resulting errors, but because it does not have the access to the deployment pipeline and the EC2 VM, there's only so much it can do other than give out suggestions. Ultimately, this error needs to be handled by a user. | Prompted AI to find issues with the deployment pipeline after giving it errors. It gives the commands that needs to be ran within the VM, so right now, it needs user intervention
Italia | 2026-10-01 | Github Copilot | Fix issue with app not publishing properly to the docker containers | Modified | A lot of it was Copilot running diagnostics commands to read logs before fixing the issue. Had to continue the chat with different errors after the first few fixes did not work. Ultimately, was able to build locally and able to run. | Prompted AI to find out why my web container was not starting and keep stopping after building. After a lot of diagnostics, Copilot was able to figure out the issue and help rebuild the Docker containers and boot locally.
Kimleng | 2026-10-12 | Github Copilot | Create system design presentation for final | Modified | I still need to manually copy the presentation from Microsoft PowerPoint to Google Presentation. Additionally, I have to organize the layout | Prompted AI 1. Let read Readme.md files and understand how system is designed then create a single slide of presentation for me. 2. How to ask Microsoft Copilot to create slide in PowerPoint.
Krizma | 2026-10-06 | Claude | Iteration 2 Presentation slides - drafted from Iteration 0 & 1 slides and the iteration 1 feedback | Modified | The first draft was too narrowed down, so I asked for a version closer to Iteration 1, then a middle ground. I checked that it covered the items we lost points on in Iteration 1 before using it as a starting point. | Prompt summary: Using the Iteration 0 and 1 slides in the drive, create slides for Iteration 2 and include what we lost points on. Output summary: Slides covering Iteration 2 accomplishments, estimation with planning poker, CI/CD and deployment, testing and coverage, and Iteration 3 milestones.
Krizma | 2026-10-08 | Claude | User Story #30: Product Level Sales Analysis (sub issues #38, #39) - backend endpoint, Sales by Product table, tests | Modified | I built it on the #29 branch so it could reuse the same date range and page, and retargeted the PR to develop after #29 merged. I ran ./mvnw test and npm test locally (12 new backend tests, 125 frontend tests passing), checked that products with no sales show zeros, and checked that Manager and Cashier are blocked. I opened PR #144 myself. | Prompt summary: Build the product level sales analysis on top of #29, following the same structure. Output summary: GET /api/v1/reports/sales/products (Admin only) returning quantity sold, revenue, cost and profit per product from the sale-time prices, sorted by profit. A sortable Sales by Product table on the Sales Report page, with backend and frontend tests.
Krizma | 2026-10-12 | Claude | Final Presentation slides | Modified | I supplied the vision text and my Requirement Leader content. I checked the AI percentages against the AI log and the code headers, and asked for the AI Usage slide to be simplified to plain text in the same fonts and colors. | Prompt summary: Make my slides look like the System Design slide, add a Project Vision slide, and summarize the team's AI usage. Output summary: Three slides in the final deck. AI Usage metrics: about 85% AI-assisted code (headers in 137 files), 86% tests, 66% documents; 46 log entries, mostly Gemini, Copilot and Claude.
Krizma | 2026-10-12 | Claude | Progress Report Review - rafted my week 6 entry, the Iteration 3 summary row, and these AI log entries | Modified | Drafting information based on what I provided in terms of my work completed this week, and I modified what was outputted and pasted it into the progress report documentation. | Prompt summary: Using the repo, meeting minutes and sheet, draft my week 6 row, the Iteration 3 summary and my new AI log entries. Output summary: Draft text and hours for each cell, issue counts for 10/6-10/12, and the story list for the story points total.
Italia | 2026-10-08 | Github Copilot | User story #46: Execute Sale | Modified | Separated this into two parts: frontend and then backend. Had to modify the frontend a bit to perform what were the requirements in the user stories. The backend had to modify and guide to make sure that it attached correctly to the frontend and met the requirements | Prompted Copilot to build the frontend based on the prototype and also made sure it adhered to overall theme. Guided AI to allow the search bar to search by text and not just barcode. Guided AI to do UI validation for adding products, insufficient payment, authorization, etc. For backend, needed to make sure that it matches with what the frontend was doing specifically to the searching. Also guided AI to add methods for write operations to correct tables
Italia | 2026-10-12 | Github Copilot | Updating testing yml to include new features that were added in iteration 3 for test coverage summary | Accepted | No modification were needed after the initial prompt as the change were succinct and did what it was asked | I prompted Copilot to check the two test yml files and cross reference it with the directory tree to see if there should be an additional categories added.
Italia | 2026-10-09 | Gemini | Creating favicon | Modified | Gemini did a decent job, but needed guiding to make sure that the icon was done correctly as what the initial prompt asked it to | Prompted AI to create a favicon that has bluejay and cart that works for a POS web application. Gemini gave several outputs, and I choose one that looks correct and gave it additional prompts to make it look more like a POS application rather than just a blue jay
Italia | 2026-10-12 | Deek Seek | Creating system test table for iteration 3 in STD | Accepted | Didn't to modify anything after giving it the HTML block for iteration 3. It was able to parse perfectly | https://chat.deepseek.com/share/v6xipyi6yhq1o1wno5
Sara | 2026-10-10 | Gemini | Developed Angular navigation filtering, Vitest unit tests, user management APIs, and user directory UI. | Accepted | Directed model to refactor tests to Vitest, fix property-to-getter bugs, split user module files, and add inline row editing. | Implemented role-based sidebar link filtering and administrative user management with inline role/status editing.
Sara | 2026-10-11 | Gemini | Generated a User Story and Acceptance Criteria for editing inventory records and adding sales prices. | Accepted | Requested a user story based on uploaded UI screenshots to guide new inventory editing features. | Created a user story and acceptance criteria for adding sales prices and inline/modal editing to the inventory page.
Sara | 2026-10-11 | Gemini | Configured AWS Parameter Store for Spring Boot secrets and set up Docker Compose local/production environments. | Accepted | Directed model to configure AWS SSM Parameter Store, troubleshoot CORS/Spring Cloud AWS issues, and write PR hand-off notes. | Configured AWS Parameter Store for secure database/JWT credential management and set up local Docker isolation.
Sara | 2026-10-11 | Gemini | Generated structured Meeting Minutes from a Zoom transcript and summary document. | Accepted | Provided a link to a Zoom transcript and requested a specific structured format for meeting minutes. | Compiled and formatted Iteration 3 meeting minutes covering feedback, action items, and video submission deadlines.
Sara | 2026-10-11 | Gemini | Resolved Spring Boot disabled user authentication bugs and implemented Angular frontend error handling. | Accepted | Instructed the model to analyze my service implementations, map backend exceptions to HTTP 401, and add Angular error banners and interceptors. | Fixed account locking vs. disabled user logic in Spring Security and added Angular login error notifications.
Sara | 2026-10-12 | Gemini | Developed piecewise stock health bar math, inline editing endpoints, and UI icon controls for POS inventory. | Accepted | Directed the model to simplify stock scaling formulas, enforce custom inline AI attribution headers, create Spring Boot PATCH endpoints, and add Material icon buttons. | Implemented piecewise inventory health scaling, Angular inline price/low-stock editing, Spring Boot PATCH endpoints, and Material UI controls.
Sara | 2026-10-12 | Gemini | Updated Spring Boot Java and Angular Vitest test classes for inventory and product management features. | Accepted | Instructed the model to update existing test classes for new API paths, fix failing MockMvc tests, add unit tests for shared components, and append AI attribution comment headers. | Updated backend and frontend unit test suites across inventory and product modules and generated a detailed PR description.
Sara | 2026-10-12 | Gemini | Created a structured System Test task covering inventory sales prices and product low stock threshold editing. | Accepted | Asked the model to map my user story acceptance criteria to a system test template and corrected the postconditions section to reflect permanent database state changes. | Created a system test task for inline inventory/product editing and refined postcondition data state rules.
Sara | 2026-10-12 | Gemini | Refined technical software testing documentation for backend (JUnit 5/Mockito) and frontend (Vitest/Angular) strategies. | Accepted | Requested high-level one-paragraph summaries for both backend and frontend testing sections based on our actual code patterns. | Developed technical test documentation for Spring Boot and Angular, then summarized it into concise team project overviews.
Sara | 2026-10-12 | Gemini | Generated security presentation outlines, AWS Parameter Store integration details, and slide speaking scripts. | Accepted | Corrected the AI from AWS Secrets Manager to AWS Parameter Store and instructed it to compress detailed points into one concise paragraph per slide. | Created a security presentation outline and script highlighting JWT token handling, stateless sessions, and AWS Parameter Store secrets integration.
Sara | 2026-10-12 | Gemini | Formatted a 3-slide Project Management outline and presentation script covering agile roles, GitHub Kanban boards, AWS outage risks, and lessons learned. | Accepted | Instructed the AI to skip generating visual slides, remove code quality/assurance sections covered by another teammate, and consolidate the remaining points into 3 slides. | Structured project management presentation content focusing on agile iteration evolution, role definitions, and cloud infrastructure risk management.

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Italia Tran | Section 6 |  |  | Section 1, 2, 3, 4 | Iteration 1, Iteration 2 | - Story #32: User view list and new user creation - Story #46: Execute sale - Added favicon to the app | - Added frontend and backend unit tests for story #32 - Added frontend and backend unit tests for story #46 - Added system test template for each user story for iteration 2 and 3 | -Updated test yml files to include code coverage summary | - Created presentation for iteration 1 and 2 - Reminded teammates to write their system test and pass it back to me for final validation - Founded issue with deployment pipeline failing to deploy to prod - Reviewed and approved PR promptly to delay any merging issues
Kimleng Lim | Section 2, Section 3.a, Section 4.b |  | Section 1, 2, 4, 5, 9 |  | Iteration 3
Krizma Nagi | - Section 3.2 - Translated all 24 SPPP features into the product backlog and kept story labels identical to the SPPP wording - Risk register updates for the final iteration: rescored risks that occurred (improper planning, deployment), corrected execution summaries, added security, blocked-task and stories-not-reaching-Done risks | - Requirement Leader: built the full product backlog in GitHub Projects (#32) covering all 24 SPPP features (Essential, Desirable, Existing, Optional) - Audited the board against the SPPP: filled the gaps and removed 15 duplicate stories - Defined 6 epics: User Authentication & RBAC, Catalog & Stock Management, POS Checkout, Sales & Financial Reporting, AI-Driven Automation, Multi-Location Expansion - Drafted the missing user stories: Admin Preloading, Core Inventory Report, Inventory Report by Date Range, Stock Entry Validation, and the optional features - Wrote user stories with tasks and Given/When/Then acceptance tests, including Sale Report by Date Range (#29) and Product-Level Sale Analysis (#30) - Led story point estimation with planning poker for every story - Scope changes with the team: core POS before AI features, low-stock alerts moved to managers, separate reports combined into one - Iteration 3: tracked story and test-story status so stories moved to Done only after their system test passed | - Section 4.7 Sales Report (sales summary and Sales by Product table) - TokenBlacklistService entry in the security components table (6.2) |  | - Iteration 2: drafted the slides from the Iteration 0 and 1 decks, including the items we lost points on in Iteration 1 - Final presentation: created the slide deck in Google Drive and assigned sections to each member - Final presentation slides: Project Vision, Requirements (Requirement Leader role), and project-wide AI Usage summary (AI contribution to code, tests and documents, tools used, reflection) - Created the Final Project Videos folder; compiled the final presentation video and the code walkthrough/demo video | - Feature #18 Cashier Session Expiration and Lockout (PR #79): server-side token revocation (TokenBlacklistService, updates to JwtAuthenticationFilter and AuthController), 15-minute idle timeout, logout flow, logged-out confirmation message - Story #57 Core Inventory Report (PR #100): Admin/Manager report endpoint, Angular Reports page, fix so unauthorized requests return 403 instead of 500 - Story #29 Sales Report by Date Range (PR #133, sub-issues #40, #41): Admin-only endpoint for revenue, cost, net profit, transactions and units sold using sale-time prices; date validation returning 400; Angular sales report page with date presets - Story #30 Product Level Sales Analysis (PR #144, sub-issues #38, #39): Admin-only per-product endpoint (quantity sold, revenue, cost, profit, sorted by profit); sortable Sales by Product table on the Sales Report page - Code reviews: PR #146 (#19 user role and enabled status), found the disabled-user 500 error that was fixed in PR #152 | - Feature #18: 19 backend tests (JUnit/MockMvc) and 18 frontend tests (Vitest), plus component tests for the logged-out message; manual browser testing of logout, token revocation and idle timeout - Story #57: 25 backend and 30 frontend tests - Story #29: service and controller tests (date validation, inclusive end date, role access 200/401/403/400) and frontend tests; manual QA seed script (story-29-sales-seed.sql) with expected results for manual testing - Story #30: 12 backend tests (6 service, 6 controller) and frontend tests (125 passing) - System test first pass for #18 (#111), #29 (#136) and #30 (#137); found that the idle timer only starts on the dashboard page - Lab 3 TDD/BDD Red/Green demonstration on TokenBlacklistService, run locally and in Docker |  | - Backup Project Lead - Drafted the project plan and sent team reminders in Iteration 0 - Drafted Iteration 0 meeting minutes; co-wrote the progress report and README with Italia - Coordinated PR reviews with teammates and responded to review comments (PR #79, #57) - Coordinated with the team on the Execute Sale (#46) dependency for the reporting stories - Reviewed the progress report against Iteration 1 feedback and fixed hour tracking
Sara Orion | Sections 1; 2.1; 4.1; 4.3; 5; 6.4 |  | Sections 3 (created diagrams); 4 (updated screenshots to match final version); 6; 8 | Section 3 | Recorded the demos for iteration 1 and 2. For the final presentation, recorded the introduction, the security details and project management aspect | I implemented the Spring Boot starter and Spring Security with RBAC; the inventory page including stock entry, inventory health and inventory list; the inline editing for the User list, Inventory list, and Product list pages; Removed the hardcoded JWT secret and database user/password | Completed unit testing for all my implemented features, including integration testing for flyway seeded data; completed system testing for Italia's user stories regarding user management and sales transactions | Restarted AWS when the environment stopped deploying. Setup the AWS Password Store for the JWT secret and DB user/password | Posted on Discord in order to keep everyone on task and to remind people of deadlines; Setup the team meetings in Zoom and facilitated each meeting; Created meeting agendas for the first few meetings while we were still getting ramped up.
Andy Chang

## Krizma
Your Lead Roles: Requirement Leader, Backup Project Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/3/26 - 9/9/26 | 6.5 | 4.5 | 2 | 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, contribute to meeting notes & progress report docs | 2 | 1 | 0.5 | 0 | 0 | 1 | 0 | 0 | N/A | Meeting Notes, Progress Report, SPPP | N/A | N/A | 0,1,2,5 | 6
2 | 9/9/26 - 9/14/26 | 5.5 | 4 | 1.5 | 0 - SpringBoot/Angular project structure, Docker basics, JWT filter flow 1 - full backlog against the SPPP, 6 epics, missing stories, acceptance tests, story points 2 - session lockout design for feature 18 3 - Feature 18 frontend and backend 4 - 19 backend tests, and 18 frontend tests, manual browser verification 5 - team meetings, PR and reviewer coordination, progress report 6 - JDK, Node, Docker Desktop, WSL2 fix, Dickerfile/compose, DB environment variables | 1 | 1 | 0 | 0 | 0 | 0.5 | 1.5 | 0 | Claude was used for the following: - drafting user stories and acceptance tests - identifying entity classes and generating the class diagram - generating full backlog and epics - troubleshooting docker - Assisting in writitng the feature 18 code and tests - understanding the file structure in github, and what some things meant - a few github related questions regarding commands and making sure I wasn't merging anything that wasn't meant to be merged - assisted in drafting some information for the progress report documentation | - Product backlog and user stories on Github Projects (#32) - Lab 2 report (user stories, class diagrams, docker screenshots) - feature 18 (cashier session expiration and lockout), submitted as a PR to develop branch | - Docker compose file sits in code, but Spring Boot kept looking for it in code/api. The DB environment variable and SPRING_DOCKER_COMPOSE_ENABLED=false must be set in every new terminal. - Docker Desktop hit a virtualization error, a wrong package install, and Dockerfile.txt extension problem -- fixed - Execute Sale (#46) isnt' built, so the Sale and SaleLineItem entities that #29 & #30 depend on don't exist yet | - The environment variable issue is worked around with the documented PowerShell commands. - Docker issues are resolved - For #46, need to coordinate with the team on who builds the entities required for my user stories and go from there (probably will be completed by Iteration 2 deadline) | 1,2,3,4,5 | 2026-12-14
3 | 9/15/26 - 9/21/26 | 13 | 12 | 1 | 0 - SpringBoot/Angular project structure, Docker basics, JWT filter flow 1 - full backlog against the SPPP, 6 epics, missing stories, acceptance tests, story points 2 - session lockout design for feature 18 3 - Feature 18 frontend and backend 4 - 19 backend tests, and 18 frontend tests, manual browser verification 5 - team meetings, PR and reviewer coordination, progress report 6 - JDK, Node, Docker Desktop, WSL2 fix, Dickerfile/compose, DB environment variables | 1 | 1.5 | 1 | 4.5 | 1 | 1.5 | 1.5 | 0 | Claude was used for the following: - drafting user stories and acceptance tests - identifying entity classes and generating the class diagram - generating full backlog and epics - troubleshooting docker - Assisting in writitng the feature 18 code and tests - understanding the file structure in github, and what some things meant - a few github related questions regarding commands and making sure I wasn't merging anything that wasn't meant to be merged - assisted in drafting some information for the progress report documentation | - Product backlog and user stories on Github Projects (#32) - Lab 2 report (user stories, class diagrams, docker screenshots) - feature 18 (cashier session expiration and lockout), submitted as a PR to develop branch | - Docker compose file sits in code, but Spring Boot kept looking for it in code/api. The DB environment variable and SPRING_DOCKER_COMPOSE_ENABLED=false must be set in every new terminal. - Docker Desktop hit a virtualization error, a wrong package install, and Dockerfile.txt extension problem -- fixed - Execute Sale (#46) isnt' built, so the Sale and SaleLineItem entities that #29 & #30 depend on don't exist yet | - The environment variable issue is worked around with the documented PowerShell commands. - Docker issues are resolved - For #46, need to coordinate with the team on who builds the entities required for my user stories and go from there (probably will be completed by Iteration 2 deadline) | 1,2,3,4,5 | 14
4 | 9/22-9/28 | 10 | 8 | 2 | 0 - story points and estimation, TDD/BDD Red-Green cycle for Lab 3 1 - story point estimation for backlog stories (#18, #60, #14, #15, #19, #22) 3 - Feature 18 logged-out confirmation message from PR review 4 - component tests for the logout message, Lab 3 Red/Green test runs and Docker test container 5 - team meeting, PR #79 review follow-up with Sara 6 - Lab 3 Dockerfile and disposable demo branch 7 - Lab 3 TDD/BDD write-up | 1.5 | 1 | 0 | 1 | 2 | 1 | 0.5 | 1 | Claude was used for the following: - implementing the logged-out confirmation message from Sara's PR review - designing the Lab 3 TDD/BDD Red/Green demonstration and Docker test container - drafting the Lab 3 write-up - understanding story points and estimating backlog stories | - Feature 18 logged-out confirmation message (update to PR #79) - Lab 3 report (TDD/BDD example, Red/Green and Docker screenshots) - story point estimates for backlog stories | - Iteration 1 feedback: no stories had story points on the board, and none were moved to Done (#18 was still In Test) - Lab 3 needed a failing (Red) test for code that was already working | - Estimated story points with the team; [points to be added to the GitHub Projects board] - Reproduced the Red state on a throwaway branch by temporarily stubbing revoke(), then restored it and deleted the branch | 0,1,2,3,4,5,6 | 14
5 | 9/29-10/6 | 15.5 | 14.5 | 1 | 0 - report data sources (products vs. sale_items snapshots, schema changelog) 1 - reviewed acceptance criteria for #57 and #29 (sub-issues #40, #41) 2 - report endpoint design and role-based access (Admin/Manager vs. Admin only) 3 - Story #57 core inventory report and Story #29 sales report by date range, backend and frontend 4 - #57: 25 backend and 30 frontend tests; #29: frontend and backend tests, QA seed script, manual testing 5 - team meeting, responding to PR reviews from Sara and Kim, progress report updates 6 - applying patches locally, fixing file placement and build errors | 1 | 1.5 | 1 | 6 | 2.5 | 1.5 | 1 | 0 | Claude was used for the following: - implementing Story #57 (core inventory report) code and tests - debugging file placement and compile errors when applying the changes - addressing PR review comments and drafting a reply on the report data source - implementing Story #29 (sales report by date range) code, tests, and QA seed script | - Story #57 core inventory report, PR merged into develop | - Test files ended up in src/main instead of src/test when applying changes, causing confusing compile errors - PR review for #57 requested changes (remove List.copyOf(), move inline styles to .scss, add JPA TODO), and Kim questioned the report's data source | - Located and moved misplaced files using PowerShell (Get-ChildItem / Select-String), then all tests passed - Made all requested changes and replied to Kim citing the DB schema changelog; PR was merged | 1,3,4,5 | 12
6 | 10/6-10/13 | 16 | 15 | 1 | 0 - per-product profit queries, building one PR on top of another branch 1 - tracked user story and test story status in GitHub Projects (#111, #136, #137), checked stories were tested before moving them to Done 2 - designed the Sales by Product table and endpoint (#30, sub-issues #38, #39) 3 - Story #30 product level sales analysis, backend and frontend (PR #144); review updates and merge of #29 (PR #133) 4 - #30: 12 backend and 125 frontend tests passing; system test support for #18 (#111) and #29 (#136) 5 - 10/10 team meeting, PR #146 review, created the Final Project Videos folder, final presentation slides (Vision, Requirements, AI Usage), progress report 6 - rebasing #30 onto develop after #29 merged 7 - compiling the final presentation and demo videos | 0.5 | 1.5 | 0.5 | 4 | 2 | 4 | 0.5 | 2 | Claude was used for the following: - implementing Story #30 (product level sales analysis) code and tests - reviewing PR #146 (feature 19) and system testing feature 18 - updating the final presentation slides (Vision, Requirements, Deployment, AI Usage) and calculating the project-wide AI usage numbers - reviewing the SDD against the code and the Iteration 2 feedback, and drafting sections 6.4, 7, 9-12 and the table of contents - reviewing the SPPP risk register and drafting updated risk entries - drafting scripts for the presentation, code walkthrough and demo videos - drafting my progress report entries, which I edited and entered myself | - Story #29 sales report by date range, PR #133 merged into develop - Story #30 product level sales analysis, PR #144 merged into develop - SDD updates (sections 2, 5.2.4, 6, 7, 8, 9, 10-12, table of contents) - SPPP risk register updates - Final presentation slides: Project Vision, Requirements, Deployment & CI/CD, AI Usage - Final presentation, code walkthrough and demo videos - Progress report: week 6, Iteration 3 summary, AI log, project contribution | - The idle timer only starts on the dashboard page, so other pages don't time out (found during #18 system testing) - PR #146 review found a disabled user's login returned 500 instead of 401, and the JWT filter didn't check if an account was enabled - #30 was built on top of the #29 branch and had to be retargeted to develop after #29 merged - Inventory report reads products.cost_price while stock entry updates stockCost, so "latest cost" may not match the latest stock entry - Local demo: the cashier account showed admin menus because the role was changed in my local database during testing | - Idle timer: documented as a known limitation in the SDD and code walkthrough; fix is to start it in the app shell instead of the dashboard - Disabled login 500 error fixed by Sara in PR #152; the enabled check in the JWT filter is documented in the SDD as future work - #30 retargeted and merged (PR #144) after #29 merged (PR #133) - Cost column mismatch flagged to Kimleng to check - Reset the cashier role in my local database and logged in again; demo recorded with the correct roles | N/A

## Sara
Your Lead Roles: Project Lead & Security Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/3/26 - 9/9/26 | 9 | 7 | 2 | 0, 1, 5, 7 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | Used Gemini chat to brainstorm ideas to share with the team. | SPPP document; GitHub setup and deliver iteration 0 release | Communication within the team has been hit and miss. | Work with team on communication expectations | 0 - Learn expectations of project 1 - Create new user stories 2 - Start to discuss the design for the user stories 3 - Start coding to setup base structure 5 - Meet with team and help manage tasks 6 - Setup local environments 7 - Any other tasks that need to get done. | 8
2 | 9/9/26 - 9/14/26 | 12.5 | 11 | 1.5 | 0, 1, 2, 3, 5, 6, 7 | 2 | 2 | 1 | 1 | 0 | 2 | 2 | 1 | Used Gemini chat mostly when working on different tasks to brainstorm and guide my deliverables. | README.md files for different code folders; setup SpringBoot application and Flyway migration for DB; implemented security RBAC functionality. | Team engagement was lacking this week. | Gave team encouraging posts in Discord. | 0 - Learn best practices for project 1 - Organize user stories for iteration releases 2 - Discuss architecture design with Impl Lead 3 - Continue building out security functionality 5 - Lead team meetings and keep team on task 6 - Continue building out Docker configuration 7 - Any other research or necessary tasks needed for my own understanding. | 12
3 | 9/15/26 - 9/21/26 | 19 | 18 | 1 | 0, 1, 2, 3, 4, 5, 6, 7 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 1 | Continued to use Gemini chat for guidance and brainstorming. Also used it for helping me debug coding issues. | SDD document (Security section); README.md files in GitHub; organized user stories in GitHub Projects; resolved CORS connection between frontend and backend through Docker; record demo for iteration 1; deliver iteration 1 release | No issues this week. Communication and engagement is getting better. |  | 0 - Continue to learn best practices for project 1 - Continue to manage user stories and organize for each iteration 2 - Collaborate with Design & Impl Lead by reviewing UI design 3 - Continue to implement new features 4 - Write unit and integration tests along with system test plans 5 - Lead team meetings and keep team on task 6 - Collaborate with Config Lead to deploy to a cloud server 7 - Any other research or necessary tasks needed for my own progress and understanding. | 12
4 | 9/22/26 - 9/28/26 | 9 | 7 | 2 | 0, 1, 2, 3, 5, 6, 7 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | Continued to use Gemini chat for guidance and brainstorming. Also used it for helping me debug coding issues. More details in the AI Usage Log | Facilitated Story Pointing exercise; Reviewed UI Design and provided feedback; implemented unit tests for authorization functionality; Facilitated team meeting; Researched solution for removing hard coded secrets and assigned to Config Lead | No issues this week. |  | 0 - Continue to learn best practices for project 1 - Continue to manage user stories and organize for each iteration 2 - Collaborate with Design & Impl Lead by reviewing UI design 3 - Continue to implement new features 4 - Write unit and integration tests along with system test plans 5 - Lead team meetings and keep team on task 6 - Collaborate with Config Lead to deploy to fix hard coded secrets 7 - Any other research or necessary tasks needed for my own progress and understanding. | 15
5 | 9/29/26 - 10/5/26 | 16 | 15 | 1 | 0, 1, 2, 3, 4, 5, 6, 7 | 2 | 1 | 1 | 5 | 2 | 2 | 1 | 1 | Continued to use Gemini chat for guidance and brainstorming. Also used it for helping me debug coding issues. More details in the AI Usage Log | Facilitated Team meeting; Implemented inventory health & stock entry functionality; Fixed issue with login screen default; Reviewed all documentation for Iteration 2 submission; Record demo for Iteration 2; Deliver iteration 2 release | Team engagement has primarily occurred on weekends which has limited the amount of time for review and completion of functionality. |  | 0 - Continue to learn best practices for project 1 - Continue to manage user stories and organize for each iteration 2 - Collaborate with Design & Impl Lead by reviewing UI design updates 3 - Continue to implement new features 4 - Write unit and integration tests along with system test plans 5 - Lead team meetings and keep team on task 6 - Collaborate with Config Lead to deploy to fix hard coded secrets 7 - Any other research or necessary tasks needed for my own progress and understanding. | 15
6 | 10/6/26 - 10/12/26 | 18 | 16 | 2 | 0, 1, 2, 3, 4, 5, 6, 7 | 2 | 1 | 1 | 5 | 3 | 1 | 2 | 1 | Continued to use Gemini chat for guidance and brainstorming. Also used it for helping me debug coding issues. More details in the AI Usage Log | Facilitated Team meeting; Implemented editing sale price and other table inline editing; Removed secrets and DB credentials from git repo; Restarted AWS instance when SSH stopped working; Created video clips for the final presentation and demo/code walk through videos; Reviewed all documentation for Iteration 3 submission; Delivered iteration 3 release | We discovered a design gap that needed to be implemented, We also continued to have issues with AWS deployment and stability | I created a new user story for the design gap of being able to edit the sale price and implemented it. I also was able to log into AWS and restart the instance in order to fix the deployment. | Final Week.

## Andy
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2/2026-9/9/2026 | 5.25 | 3.75 | 1.5 | 0,1,2,5 | 2 | 0.5 | 0.25 | 0 | 0 | 1 | 0 | 0 | google.ai | Demo and Video | N/A | Config CI/CD | 6 - config github ci/cd | 6
2 | 09/10/2026-09/20/02026 | 5 | 4 | 1 | 2,3,6 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | google.ai | CI/CD | NA | Config CI/CD | 6 - config github actions | 4
3 | 2026-09-26 | 2 | 2 |  | 0,6 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | google.ai | CI/CD - Set up completed CI for both frontend and backend. Set up a EC2 server for CD and working (http://18.191.186.72:4200) | N/A | Fix any issues for CI/CD | 0 - learning 6 - configuration | 3
4 | 2026-10-04 | 3 | 3 |  | 0,2,3 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | google.ai | Implement user stories, front end UI work and backend API work | N/A | Implement user stories | 3 | 3
|  | 0 | 0
|  | 0 | 0

## Kimleng
Your Lead Roles: Design & Implementation Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/05-09/09 | 6.5 | 4.5 | 2 | 0 - How to getting started with Spring Boot and MVC 1 - define high level functional requirements, 5 - Setup first kick off meeting | 1 | 3 | 0 | 0 | 0 | 0.5 | 0 | 0 | Use ChatGPT and Gemini for text formating, structuring, correcting grammar, and brainstorming new features for project. | 1. Section 2 (Related Work), Section 3.a (Existing Features baseline) & Section 4.b (Risk Management Summary) 2. Set up git and project board on GitHub |  |  | 2,3 | 6
2 | 09/09-09/23 | 16 | 13.5 | 2.5 | 0 - How to setup Java ecosystem development environment and Docker 1 - Analysis product catalog and inventory managment requirement for creating user story and task in GitHub project 3 - Add Bluejay web ui project and implement screen including login form and simple dashboard. 5 - Post a software architecture draft design on Discord and conduct code reviews 7 - Fill out SDD documentation | 2 | 3 | 0 | 1 | 0 | 2.5 | 0 | 5 | Use AI tools for evaluation technologies, write good user story and task | 1. Add user story and task into icebox 2. Fill in SDD sections including introduction, software architecture, REST APIs, Database Design, and UI Design |  |  | 2,3 | 12
3 | 09/23/-10/07 | 24.5 | 21 | 3.5 | 0 - Learning about TDD for Lab exercise 2 - design product catalog APIs 3 - Implement product catalog APIs, services, and components 4 - Test product catalog components, APIs controller, and services 5 - Participate in standup meeting to estimate story points | 3 | 0 | 4 | 8 | 4 | 2 | 0 | 0 | Use GitHub Copilot for implementation details including JPA repository, API controller, components, and tests. | 1. Project catalog management 2. Meeting minutes 3. SDD updates |  |  | 2,3,4 | 8
4 | 10/07-10/13 | 11.5 | 10 | 1.5 | 0 - How to record product demo on Zoom and Microsoft Teams 3 - Implement tech debt in reports features 4 - Test excute sale feature and give feedback on PR 5 - Create presentation video and slide | 2 | 0 | 0 | 3 | 1 | 4 | 0 | 0 | Use GitHub Copilot and Microsoft Copilot for presentations | 1. Final presentation |  |  | 0 | 0

## Italia
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/02-09/09 | 3.5 | 2.5 | 1 | 4 - Added testing section to SPPP 6 - set up git 7 - research unit testing frameworks, coding practices | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0.5 |  | 1. Wrote section 6 of SPPP 2. Added to the team README for the project | 1. Need to finalize testing framework with team and update as necessary | 1. In our next meeting, should dedicate a part of it to flesh out the testing section and see how everyone is comfortable with it. | 4. Update the testing section of SPPP after getting team member's approval | 2
2 | 9/9/26 - 9/22/26 | 6.5 | 5.5 | 1 | 1 - Added version 1.0.0 of the STD 4 - Started adding system test tasks in github 5 - Attended weekly meeting and facilitated within the discord chat 6 - Built and run the project locally | 0 | 2 | 0 | 0 | 1 | 1 | 1.5 | 0 | Used Deek Seek to help get a list of all story tasks in the github project to use for the STD manual testing table | 1. Wrote the STD 2. Added a system test template for future use in Github 3. Added user stories that were assigned to me during week 1 on Github for tracking | 1. Need to fix issue with docker containers not building correctly locally | 1. Will dedicate a time to fix the build issue | 1. Majority of the time will be coding the assigned user stories and unit tests. 2. Update the STD/SPPP as necessary 3. Add system tests to each individual user story and assigned it to the respective individual | 20
3 | 9/23/26 - 10/6/26 | 19.5 | 16 | 3.5 | 3 - Implemented user list view and user creation 4 - Implemented testing for the API and front end tests for the user list page and the user creation page. Updated both testing yml files to include testing summary for each PR checks 5 - Attended weekly status meetings. Reminded teammates to do testing 6 - Added code in attempt to fix issue with deployment pipeline failing. Fixed issue with local not deploying and containers not being created 7 - Added system test template for each user story for iteration 2 | 0 | 0 | 0 | 5 | 5 | 0 | 4 | 2 | Used Github Copilot to do user story coding, amending the yml files. Fixed Docker containers not building correctly. Attempted to fix issue with deployment pipeline, but needs user intervention | 1. Updated STD to fit iteration 2 2. Worked on user story #32 (user view, user creation) 3. Updated testing yml to include summary report after each PR build 4. Added system test template for each user story for iteration 2 5. Worked with Krizma on presentation slide and video | 1. Deployment pipeline is still broken. Needs user intervention. | 1. Work with Andy to see if we can remedy this issue | 1. Majority of the time will be spent working on completing assigned user stories for iteration 3 2. Work on the final presentation video and slide 3. Fix deployment pipeline 4. Possibly update the testing yml to create a better summary view (if time presents itself) | 12
4 | 10/7/26 - 10/13/26 | 15.5 | 12 | 3.5 | 3 - Implemented sales page and executing a sale, fixed bug with null category for products 4 - Implemented unit tests for frontend/backend of the sales page. Added system tesk task for all user stories in iteration 2 and 3 5 - Reminded teammates to write their own system test, do said test, and then pass it back to me for final validation 6 - Updated testing yml to include any new features and enhancements that were done in iteration 3 | 0 | 0 | 0 | 4 | 5 | 2 | 1 |  | Used GitHub Copilot as the main AI tool to implement the sales page, amending the test yml files, triaging issues with builds and testing | 1. Updated STD to reflect final automated testing data 2. Worked on user story #46 (executing sales), fixed bug with null categories for products 3. Updated testing yml to include new features that were created in iteration 3 4. Added system test template for each user story in iteration 3 5. Did final validation check for all system tests | None | None | N/A | N/A